## Slide 1
Partner Exchange
Offence Management
Registration and Vehicles
Payment Modernisation
Transport Services for Business Customers
FMP Discovery
Off Mgmt Data Governance, model
and Ownership
IAP IIPS
Vehicle Register
Customer Refunds
New ways to pay
Rego related e-notifications
Rego enquiry online
Pay Rego online
Business ID to TMR Account
CRM Requirements Discovery
Registration Enquiry Service
Customer Account
Pricing engine fee management
Modernised NEVDIS Integrations
NHVR Work
NDFLRS
Subsid ledger
Quote tool PoC
R &VM Data Governance, model
and Ownership
Payment Data Governance, model
and Ownership
TS4Bus Data Governance, model
and Ownership
Kirsty
Kirsty
Kirsty
Kirsty
Kirsty

## Slide 3: Key Discovery Deadlines
Initiative | Suggested Discovery Completion | Key Driver
QRO IAP / IIPS Modernisation | Dec 2026 | Technology risk, RL&S onboarding, IIPS decommission planning
Chequexit / WoG Payment Platform | Dec 2026 | Government cheque retirement milestones begin from 2026
NHVR Strategic Access Model | Dec 2026 | Existing MoU obligations and stakeholder demand
NDLFRS | Mar 2027 | 1-2 year implementation lead time and national participation decision
Business Portal (Transport Org Customer Servicing) | Mar 2027 | Identity, access and service prioritisation required before build decisions
Registration & Vehicle Data Governance | Mar 2027 | Foundational capability supporting APIs, portal and data sharing
Registration Enquiry Modernisation | Mar 2027 | Existing roadmap commitments and legacy reduction opportunities
Customer Refunds | Mar 2027 | Dependent on payment modernisation direction
New Ways to Pay | Mar 2027 | BPoint migration and merchant platform changes
Modernised NEVDIS Integrations | Jun 2027 | National dependencies and API/event architecture
Vehicle Register Modernisation | Jun 2027 | Dependent on data mastering and future-state architecture
Fines Modernisation Project (FMP) | Jun 2027 | Separation of infringement capabilities from TRAILS
Customer Account Capability | Jun 2027 | Depends on strategic payment platform decisions
Pricing Engine / Fee Management | Sep 2027 | Depends on payment, customer account and fee policy decisions
Quote Tool PoC | Sep 2027 | Depends on pricing and customer account capabilities

## Slide 4: Recommended Discovery Waves
Group discoveries by target completion date, from externally committed work through dependent capabilities.
WAVE 1
By Dec 2026
COMMITMENTS & RISK
• QRO IAP / IIPS Modernisation Technology risk and decommissioning
• Chequexit / WoG Payments Government cheque-retirement mandate
• NHVR Access Strategy MoU obligation and stakeholder demand
WAVE 2
By Mar 2027
SERVICE FOUNDATIONS
• NDLFRS Participation decision
• Business Portal Identity and service scope
• Data Governance Enables APIs and sharing
• Rego Enquiry Legacy reduction roadmap
• Customer Refunds Payment direction
• New Ways to Pay BPoint migration
WAVE 3
By Jun 2027
CORE ARCHITECTURE
• Modernised NEVDIS National API and event architecture
• Vehicle Register Data mastering dependency
• Fines Modernisation Project Separates infringements from TRAILS
• Customer Account Depends on payment platform
Decision point: approve Wave 1 funding now and confirm Wave 2 sponsorship before December 2026.
WAVE 4
By Sep 2027
DEPENDENT CAPABILITIES
• Pricing / Fee Management Payment, account and policy dependency
• Quote Tool PoC Depends on pricing and account

## Slide 5: Main Discovery Questions
1. Customer & Business Outcomes
• What problem are we trying to solve?
• Who receives the most value?
• What customer pain points exist today?
• What outcome will improve if we do this?
• What happens if nothing changes?
6. Stakeholders
• Who owns the business outcome?
• Who owns the systems?
• Which external partners are involved?
• Which agencies need to be consulted?
• Who will approve investment decisions?
2. Drivers & Deadlines
• Is there a legislative or regulatory driver?
• Is there a national initiative dependency?
• What external deadlines exist?
• What organisational commitments already exist?
• What risks increase if we delay?
7. Architecture & Integration
• What systems need to integrate?
• Are APIs available?
• Is event streaming required?
• Are there national interoperability requirements?
• What technology constraints exist?
3. Current State
• How does the process work today?
• Which systems are involved?
• Where are the biggest manual activities?
• Where are the greatest technology risks?
• What technical debt currently exists?
8. Risks
• What is the current operational risk?
• What is the technology risk?
• What is the customer impact risk?
• What is the regulatory/compliance risk?
• What are the risks of delaying investment?
4. Information & Data
• What information is required?
• Who owns the information?
• What is the system of record?
• What data quality issues currently exist?
• What data sharing obligations exist?
9. Dependencies
• What other initiatives must happen first?
• What shared capabilities are required?
• Are there funding dependencies?
• Are there platform dependencies?
• Are there organisational change dependencies?
5. Future-State Capability
• What business capability are we trying to create?
• What should remain within TRAILS/RnLS?
• What should become a separate service?
• What should be API-enabled?
• What should be customer self-service?
10. Measures of Success
• How will success be measured?
• What customer behaviour should change?
• What operational metrics should improve?
• What costs or risks should reduce?
• What legacy capability could be retired?

## Slide 6: Offence Management
Offence Management Data Governance, Model and Ownership
FMP Discovery
IAP IIPS

## Slide 7
Offence Management
Business Process & Operating Model
Product Management & Governance
Requirements & Design
Change Impact & Business Readiness
Benefits Realisation
Planning & Control
Product Description
Risk, Issue & Assurance
Change & Configuration Control
Closure & Continuous Improvement
Current State & Requirements
Delivery Plan
Solution Design
Process Design
Policy, Structure & Procedures
Impact Assessment
Readiness & Adoption
Benefits Planning
Risk Register
Issue Register
Quality Register
Assumptions Log
Configuration Item Record
Change Register
Acceptance / Sign-off Record
Lessons Learned Log
Current State Assessment
Business Requirements
Functional Specification
Technical Specification
Business Process Maps
Target Operating Model
Revised Policies & Procedures
Org Structure & RACI Changes
Change Impact Assessment
Business Readiness Assessment
User Work Instructions
Benefits Realisation Plan
Off Mgment Data Governance, Model & Ownership
FMP Discovery
IAP IIPS

## Slide 8
Offence Management
Off Mgmt Data Governance, Model & Ownership
FMP Discovery
IAP IIPS
Design
Delivery
Discovery
Discovery
Discovery
Design
Transition
Business Discovery
Governance Discovery
Architecture Discovery
Dependency Discovery
Stakeholder Analysis
Current State Assessment
Process Assessment
Governance Assessment
Decision Framework
Ownership Assessment
System Landscape Assessment
Integration Assessment
QRO Dependency Map
Legislative Assessment
Funding Assessment
Design
Governance Design
Future Operating Model
Governance Framework
Ownership Model
Data Design
Data Governance Model
Information Model
Delivery
Governance Implementation
Data Implementation
Governance Artefacts
Committee Structures
Management Process
Data Standards
Ownership Controls
Transition
Adoption Plan
Communications Plan
Benefits Baseline
Delivery
Future State Service Design
Integration Design
Interface Enhancements
Service Enhancements
Business Discovery
Current Process Assessment
User Assessment
Technical Discovery
Interface Assessment
Service Assessment
Integration Assessment
Risk Discovery
Gap Analysis
Risk Assessment
Transition
Release Readiness Assessment
Operational Handover
Business Discovery
Current Process Assessment
User Assessment
Technical Discovery
Interface Assessment
Service Assessments
Integration Assessment
Risk Discovery
Gap Analysis
Risk Assessment
Future State Service Design
Integration Design
Interface Enhancements
Service Enhancements
Release Readiness Assessment
Operational Handover

## Slide 9: Offence Management Discovery
Purpose
Define the future Offence Management capability: establish trusted data foundations, clarify the role of infringement processing services, and separate infringement functionality from TRAILS.
Why now
IAP expansion, IIPS technology risk, FMP planning and TRAILS modernisation require a clear future-state strategy. Discovery must resolve scope, ownership, architecture, integration reuse and decommissioning.
Discovery decisions
• What stays in TRAILS/RnLS, and what moves to modernised or external platforms?
• How will offence data be governed and mastered?
• How should FMP, IAP and QRO fit together?
• What systems, integrations and online services can be reused, simplified or retired?
Required outputs
• Capability model plus data governance and ownership framework
• FMP options and end-to-end offence journey architecture
• TRAILS impact assessment and IIPS decommissioning pathway
• Risk register, delivery roadmap and implementation estimate
Discovery window
December 2026 → June 2027
Work in scope
Offence Management data governance, model and ownership • FMP Discovery • IAP / IIPS

## Slide 10: Discovery Focus by Initiative Offence Management
QRO IAP / IIPS
IIPS decommission pathway?
Integration requirements?
RL&S onboarding approach?
Future offence administration platform?
Discovery Commitment (Tash supplied)
Technical scope definition based on QRO requirements
Technical Options Analysis (for example, all offences, fiscal penalties only and impact on TRAILS)*
End to End to be architecture diagrams for each RnLSoffence journey type (High level design/ physical architecture)*
A clear position on technical reuse including TCO analysis (for integrations)*
TRAILS impact analysis
TRAILS decommissioning plan
RnLSRisk Register (including opportunities)
Implementation plan for RnLScomponents of delivery including resource, timeframe and estimate (including decommissioning of online services)

## Slide 11: Registration and Vehicle
Registration and Vehicle Data Governance, Model and Ownership
Registration Enquiry Service
Vehicle Register

## Slide 12
Registration & Vehicles
Business Process & Operating Model
Product Management & Governance
Requirements & Design
Change Impact & Business Readiness
Benefits Realisation
Planning & Control
Product Description
Risk, Issue & Assurance
Change & Configuration Control
Closure & Continuous Improvement
Current State & Requirements
Delivery Plan
Solution Design
Process Design
Policy, Structure & Procedures
Impact Assessment
Readiness & Adoption
Benefits Planning
Risk Register
Issue Register
Quality Register
Assumptions Log
Configuration Item Record
Change Register
Acceptance / Sign-off Record
Lessons Learned Log
Current State Assessment
Business Requirements
Functional Specification
Technical Specification
Business Process Maps
Target Operating Model
Revised Policies & Procedures
Org Structure & RACI Changes
Change Impact Assessment
Business Readiness Assessment
User Work Instructions
Benefits Realisation Plan
R&VM Data Governance, Model and Ownership
Registration Enquiry Service
Vehicle Register

## Slide 13
Registration and Vehicles
R&VM Data Governance, Model and Ownership
Registration Enquiry Service
Vehicle Register
Design
Delivery
Discovery
Discovery
Discovery
Design
Delivery
Design
Delivery
Transition
Business Discovery
Current Ownership Assessment
Stakeholder Assessment
Governance Discovery
Governance Framework Assessment
Ownership Assessment
Data Discovery
Data Asset Assessment
Data Quality Assessment
Governance Design
Target Governance Model
Ownership Framework
Data Design
Data Domain Model
Data Ownership Model
Governance Artefacts
Data Quality Controls
Ownership Processes
Governance Adoption
Monitoring Framework
Transition
Customer Discovery
Service Discovery
Technical Discovery
User Needs Assessment
Journey Assessment
Current Service Assessment
Channel Assessment
Integration Assessment
Architecture Assessment
Service Design
Future Service Model
Functional Requirements
Solution Design
Technical Design
Integration Design
Enquiry Services
Integration Services
Portal Services
Training Materials
Operational Support Model
Transition
Business Discovery
Register Capability Assessment
Data Discovery
Technical Discovery
User Assessment
Data Model Assessment
Data Quality Assessment
Platform Assessment
Integration Assessment
Future Register Design
Information Architecture
Register Components
Data Migration Products
Reporting Components
Register Operational Model
Support Model

## Slide 14: Registration and Vehicles Discovery
Purpose
Define the future Registration and Vehicle capability: establish trusted data foundations, modern enquiry services and an authoritative vehicle register supporting digital services, customer channels and partner exchange.
Why now
Registration and vehicle information underpins Business Portal, registration APIs, RegoCheck modernisation, Partner Exchange and NEVDIS. Discovery must resolve data ownership, service boundaries, enquiry patterns and register management.
Discovery decisions
• What registration and vehicle data should be mastered and governed in the domain?
• How should information be exposed through APIs, digital services and partner channels?
• What should RegoCheck, enquiry services and the Vehicle Register own and publish?
• What legacy enquiry services and mainframe dependencies can be reduced?
Required outputs
• Capability model plus data governance and stewardship framework
• Registration Enquiry Service strategy and Vehicle Register definition
• API and event catalogue plus system-of-record assessment
• Legacy reduction opportunities, roadmap and sequencing plan
Discovery window
March 2027 → June 2027
Work in scope
Registration and Vehicle data governance, model and ownership • Registration Enquiry Service • Vehicle Register

## Slide 15: Discovery Focus by Initiative Registration and Vehicle
Registration Enquiry
API consumers?
RegoCheck replacement strategy?
Event-driven opportunities?
Legacy retirement opportunities?

## Slide 16: Payment Modernisation
Payment Data Governance, Model and Ownership
Customer Refunds
New ways to pay
Subsid Ledger
Customer Account
Pricing engine fee management
Quote tool PoC

## Slide 17
Payment Modernisation
Business Process & Operating Model
Product Management & Governance
Requirements & Design
Change Impact & Business Readiness
Benefits Realisation
Planning & Control
Product Description
Risk, Issue & Assurance
Change & Configuration Control
Closure & Continuous Improvement
Current State & Requirements
Delivery Plan
Solution Design
Process Design
Policy, Structure & Procedures
Impact Assessment
Readiness & Adoption
Benefits Planning
Risk Register
Issue Register
Quality Register
Assumptions Log
Configuration Item Record
Change Register
Acceptance / Sign-off Record
Lessons Learned Log
Current State Assessment
Business Requirements
Functional Specification
Technical Specification
Business Process Maps
Target Operating Model
Revised Policies & Procedures
Org Structure & RACI Changes
Change Impact Assessment
Business Readiness Assessment
User Work Instructions
Benefits Realisation Plan
Payment Data Governance, Model & Ownership
Customer Refunds
New ways to pay
Subsid ledger
Customer Account
Pricing engine fee management
Quote tool PoC

## Slide 18
Payment Modernisation
Subsid ledger
Customer Account
Payment Data Governance, Model & Ownership
Customer Refunds
New ways to pay
Pricing engine fee management
Discovery
Design
Delivery
Discovery
Design
Delivery
Discovery
Design
Delivery
Discovery
Discovery
Design
Delivery
Design
Delivery
Quote tool PoC
Discovery
Design
Delivery
Transition
Discovery
Design
Delivery
Transition
Payment Data Assessment
Ownership Assessment
Governance Assessment
Payment Data Model
Governance Design
Data Standards
Governance Controls
Monitoring Processes
Refund Process Assessment
Customer Pain Points
System Assessment
Future Refund Process
Rules Design
Refund Services
Workflow Components
User Guidance
Operational Support
Transition
Payment Method Assessment
Customer Research
Market Review
Future Payment Capability
Channel Integrations
Payment Services
Chennel Integrations
Customer Adoption Plan
Transition
Subsidy Assessment
Financial Process Assessment
Data Assessment
Ledger Design
Reporting Design
Ledger Components
Reporting Components
Finance Operational Model
Transition
Customer Discovery
Technical Discovery
Identity Assessment
Account Assessment
Journey Assessment
Authentication Assessment
CRM Assessment
Customer Account Model
Identity Model
Account Services
Profile Services
Identity Services
Customer Migration
Support Model
Transition
Pricing Process Assessment
Fee Assessment
Legislative Assessment
Pricing Rules Model
Fee Management Design
Pricing Engine
Rules Services
Administrative Procedures
Transition
Business Need Assessment
Feasibility Assessment
PoC Design
Quote Tool Prototype
Evaluation Metrics
Recommendation Report

## Slide 19: Payment Modernisation Discovery
Purpose
Define the future payments ecosystem across customer payments, refunds, accounts, pricing, quoting and financial processing—aligned with government-wide payment reform and Chequexit obligations.
Why now
Whole-of-government reform, cheque retirement deadlines, merchant platform changes and payment orchestration decisions require a clear target architecture and future customer financial experience.
Discovery decisions
• What should the target payment operating model and architecture be, aligned with the future WoG platform?
• How should refunds, customer accounts and payment channels work together?
• Which capabilities should be modernised, and which should be replaced?
• How can dependency on cheque processing be removed?
Required outputs
• Payment capability model plus Chequexit impact assessment
• Architecture options and financial integration roadmap
• Refund modernisation strategy plus Customer Account definition
• Pricing and quoting assessment plus investment sequencing
Discovery window
December 2026 → September 2027
Work in scope
Payment data governance, model and ownership • Customer Refunds • New Ways to Pay • Subsid Ledger • Customer Account • Pricing Engine / Fee Management • Quote Tool PoC

## Slide 20: Discovery Focus by Initiative Payment Modernisation
Payment Modernisation
Future WoG platform alignment?
Refund orchestration?
SAP integration impacts?
Chequexit transition approach?
Customer Refunds
Visibility of entitlements?
Digital refund requests?
Settlement processes?
Customer journey improvements?
Customer Account
Single customer financial profile?
Transaction history requirements?
Payment preference management?
Pricing Engine
Fee ownership?
Fee calculation rules?
Legislative change management?

## Slide 21: Transport Services for Business Customers
TS4Bus Data Governance, Model and Ownership
CRM Requirements Discovery
Business ID to TMR Account
Rego Related eNotifications
Rego Enquiry Online
Pay Rego Online

## Slide 22
Transport Services for Business Customers
Business Process & Operating Model
Product Management & Governance
Requirements & Design
Change Impact & Business Readiness
Benefits Realisation
Planning & Control
Product Description
Risk, Issue & Assurance
Change & Configuration Control
Closure & Continuous Improvement
Current State & Requirements
Delivery Plan
Solution Design
Process Design
Policy, Structure & Procedures
Impact Assessment
Readiness & Adoption
Benefits Planning
Risk Register
Issue Register
Quality Register
Assumptions Log
Configuration Item Record
Change Register
Acceptance / Sign-off Record
Lessons Learned Log
Current State Assessment
Business Requirements
Functional Specification
Technical Specification
Business Process Maps
Target Operating Model
Revised Policies & Procedures
Org Structure & RACI Changes
Change Impact Assessment
Business Readiness Assessment
User Work Instructions
Benefits Realisation Plan
TS4Bus Data Governance, Model & Ownership
CRM Requirements Discovery
Business ID to Customer Account
Rego Related e-notifications
Rego Enquiry Online
Pay Rego Online

## Slide 23
Transport Services for Business Customers
Rego Related e-notifications
Rego Enquiry Online
TS4Bus Data Governance, Model & Ownership
CRM Requirements Discovery
Business ID to Customer Account
Pay Rego Online
Transition
Discovery
Discovery
Design
Delivery
Discovery
Design
Delivery
Discovery
Design
Delivery
Design
Discovery
Design
Delivery
Delivery
Transition
Transition
Transition
Discovery
Design
Delivery
Transition
Business Customer Assessment
Data Ownership Assessment
Governance Model
Business Customer Data Model
Governance Controls
Data Standards
Adoption Plan
Customer Discovery
CRM Requirement Specification
CRM Backlog
Procurement Inputs
Capability Discovery
Market Discovery
Customer Journey Assessment
Persona Assessment
CRM Capability Assessment
Gap Assessment
Vendor/Internal Assessment
Options Assessment
Future CRM Architecture
Prioritised Capability Set
Delivery Road Map
Business Identity Assessment
Account Linkage Assessment
Identity Model
Access Model
Identity Services
Linking Services
Migration Strategy
Notification Assessment
Channel Assessment
Customer Research
Notification Design
Preference Management Design
Notification Services
Preferences Capability
Customer Adoption
User Research
Service Assessment
Online Service Design
Online Enquiry Capability
Operational Support
Transition
Payment Assessment
Customer Journey Assessment
Payment Experience Design
Online Payment Services
Adoption Support

## Slide 24: Transport Services for Business Customers Discovery
Purpose
Define the future digital service experience for organisation customers through trusted identity, streamlined access, digital servicing and self-service registration capabilities.
Why now
The Business Portal vision, organisation identity needs, digital communications and customer experience opportunities require a clear organisation customer model before implementation.
Discovery decisions
• What should the end-to-end organisation customer experience look like?
• How should organisations, authorised officers and delegates be managed?
• Which services should be prioritised for MVP and later releases to drive adoption and value?
• How should organisation accounts interact with payments, registrations and communications?
Required outputs
• Organisation customer capability model plus Business Portal operating model
• Customer identity and access framework plus digital communications strategy
• MVP service prioritisation plus registration self-service roadmap
• Dependency assessment plus business case and implementation roadmap
Discovery window
March 2027
Work in scope
TS4Bus data governance, model and ownership • CRM Requirements Discovery • Business ID to TMR Account • Rego-related eNotifications • Rego Enquiry Online • Pay Rego Online

## Slide 25: Discovery Focus by Initiative Transport Services for Business Customers
Organisation identity model?
Authorised officer model?
Customer account structure?
MVP service scope?
Portal ownership?

## Slide 26: Partner Exchange
Modernised NEVDIS Integrations
NHVR
NDFLRS

## Slide 27
Partner Exchange
Business Process & Operating Model
Product Management & Governance
Requirements & Design
Change Impact & Business Readiness
Benefits Realisation
Planning & Control
Product Description
Risk, Issue & Assurance
Change & Configuration Control
Closure & Continuous Improvement
Current State & Requirements
Delivery Plan
Solution Design
Process Design
Policy, Structure & Procedures
Impact Assessment
Readiness & Adoption
Benefits Planning
Risk Register
Issue Register
Quality Register
Assumptions Log
Configuration Item Record
Change Register
Acceptance / Sign-off Record
Lessons Learned Log
Current State Assessment
Business Requirements
Functional Specification
Technical Specification
Business Process Maps
Target Operating Model
Revised Policies & Procedures
Org Structure & RACI Changes
Change Impact Assessment
Business Readiness Assessment
User Work Instructions
Benefits Realisation Plan
Modernised NEVDIS Integrations
NHVR Work
NDFLRS

## Slide 28
Partner Exchange
Modernised NEVDIS Integrations
NHVR Work
NDFLRS
Discovery
Design
Delivery
Transition
Discovery
Design
Delivery
Transition
Discovery
Design
Delivery
Transition
Partner Discovery
Technical Discovery
Integration Assessment
Stakeholder Assessment
Obligation Assessment
Architecture Assessment
Future Integration Model
API Strategy
Integration Services
API Services
Partner Onboarding
Migration Plan
Current Integration Assessment
Future Exchange Design
NHVR Integration Services
Compliance Validation
Regulatory Assessment
Partner Assessment
Future Exchange Design
Exchange Services
Partner Migration
Service Assessment
Interface Services

## Slide 29: Partner Exchange Discovery
Purpose
Define the future partner exchange capability for national integration, trusted partner access and identity verification while reducing reliance on legacy integration and access arrangements.
Why now
National data exchange opportunities, NHVR access obligations and NDLFRS participation decisions require a coordinated approach to partner integration, identity and access services.
Discovery decisions
• How should registration and licensing information be exchanged with partners?
• What access model should support NHVR and other agencies, and what is required for NDLFRS?
• Which integrations should be modernised or retired?
• How should identity, privacy and data governance work across partner services?
Required outputs
• Partner Exchange capability model plus partner integration strategy
• NHVR access recommendation plus NDLFRS participation assessment
• Identity and access architecture plus data sharing and governance framework
• Integration modernisation roadmap plus funding and implementation recommendations
Discovery window
December 2026 → June 2027
Work in scope
Modernised NEVDIS Integrations • NHVR • NDLFRS

## Slide 30: Discovery Focus by Initiative Partner Exchange
NHVR
Future access model?
Federated identity approach?
Long-term operating responsibilities?
Partner access patterns?
NDLFRS
Participation model?
Privacy obligations?
Data governance?
Commercial/revenue model?
Commonwealth dependencies?
NEVDIS
Event publishing requirements?
National standards?
Existing interface retirement?
Jurisdiction dependencies?

## Slide 31: NHVR & QCIS highlight the need for a future Partner Exchange model
Why this matters
NHVR and QCIS are both surfacing the same broader challenge: external partners need ongoing access to registration and vehicle-related information, but current access and integration patterns are tied to legacy arrangements that are becoming harder to sustain. The QCIS HLE confirms QCIS currently consumes 17 RnLS web services, with options ranging from retaining existing services through to API and microservice-based approaches.
Current challenge
NHVR access is currently supported through interim ICT arrangements, including Windows 365 access for approximately 150 NHVR users, with PDU managing access requirements as an intermediary.
The July 2024 TMR-NHVR MoU requires NHVR personnel to transition away from TMR ICT services requiring direct user access, such as TRAILS and TICA, towards alternative services developed and administered by NHVR.
QCIS replacement is also dependent on access to registration data and currently relies on existing RnLS web services, creating a decision point around whether to reuse existing integrations or modernise them.
Existing partner consumers would need to be considered if services are modernised, as maintaining both existing and new integrations would create ongoing operational overhead.
Strategic insight
NHVR and QCIS should not be treated as isolated access or integration issues. They point to a broader need for a Partner Exchange capability that supports trusted partner access, identity management, modern integration patterns and reduced reliance on legacy user access models.
Discovery framing statement
The opportunity is to define a future partner access and data exchange model that enables agencies such as NHVR and QCIS to access the information they need through trusted, sustainable and modernised patterns, rather than continuing to extend legacy user access or one-off service integrations.

## Slide 32: Key discovery focus areas and decisions needed
1. Future access model
The NHVR material indicates a direction away from direct user access into TMR systems and towards services developed and administered by NHVR.
Discovery questions
Which partner use cases require direct user access versus system-to-system/API access?
Which NHVR functions currently depend on TRAILS, TICA or other TMR ICT services?
What access capabilities need to be retained, replaced or redesigned?
Should QCIS and NHVR access needs be addressed through a common Partner Exchange model?
Early discovery consideration The future access model should clarify whether the preferred pattern is partner-managed access to their own services, API-based access to TMR data, or a combination of both. This is a discovery hypothesis, not yet confirmed in the source material.
2. Federated identity and trusted partner access
The Partner Exchange material identifies trusted partner access and identity verification as a key purpose, and recognises identity and access architecture as a required discovery output.
Discovery questions
Is a federated identity model required for NHVR and other partners?
What identity assertions would TMR need to trust?
Who owns identity proofing, user provisioning and de-provisioning?
How should access be governed across partner services?
Early discovery consideration No source confirms that a federated identity solution has been selected. The evidence supports this as a key discovery question rather than a decided direction.
3. Long-term operating responsibilities
The NHVR access material highlights that the current arrangement creates operational burden because PDU is managing access requirements without dedicated resourcing.
Discovery questions
Which responsibilities should remain with TMR?
Which responsibilities should transfer to NHVR or other partner agencies?
Who owns ongoing support, access administration, onboarding and incident management?
How will operating responsibilities align with the TMR-NHVR MoU?
Early discovery consideration The MoU direction suggests NHVR should move towards services developed and administered by NHVR, but the detailed operating split between TMR and NHVR still needs to be defined.
4. Partner access patterns
The Partner Exchange artefact identifies partner assessment, current integration assessment, future integration model, API strategy, and partner onboarding/migration planning as discovery activities
Discovery questions
What partner types need access to registration and vehicle data?
Which partners use existing RnLS services today?
Which existing services should be retained, retired or modernised?
What onboarding, migration and support model should apply to future partners?
Early discovery consideration QCIS provides a useful test case because its HLE considered existing service reuse, Anypoint APIs, and a hybrid API/microservices approach.

## Slide 33: NDLFRS Participation | Strengthening Identity Security & Future Digital Services
Opportunity
Queensland has an opportunity to participate in the National Driver Licence Facial Recognition Solution (NDLFRS), part of the Commonwealth's Identity Verification Services (IVS), to provide secure, national facial verification capability while strengthening fraud prevention, privacy protection and digital service delivery.
What is NDLFRS?
NDLFRS supports the Commonwealth's Identity Verification Services ecosystem:
Document Verification Service (DVS)
Verifies biographic identity information contained in identity documents.
Face Verification Service (FVS)
Matches a customer's facial image against their identity document.
Enables secure, real-time facial verification.
Removes reliance on retaining copies of identity documents for verification.
Why it matters
Improved Identity Security
Reduces identity fraud through facial verification rather than biographic-only checks.
Supports stronger verification across government and private sector services.
Enables interstate identity verification and improved licence transfer assurance.
Stronger Privacy Protection
FVS users are not permitted to retain images used in verification.
Reduces exposure to data breaches associated with stored identity documents.
Supports improved protection of Queenslanders' personal information.
Future Digital Service Enablement
Supports Commonwealth services such as myID.
Creates opportunities for Queensland Digital Identity and Digital Licence services.
Positions Queensland within Australia's emerging digital identity ecosystem.
Strategic imperative
Other jurisdictions are already progressing implementation:
  Jurisdiction Status
  Western Australia Participating and uploaded
  South Australia Participating and preparing upload
  Victoria Expected to participate
  New South Wales Planning uploads
  Queensland Decision required
Delaying participation risks:
Loss of future revenue opportunities
Reduced access to modern identity verification services
Increased exposure to identity fraud and data breach risks
Falling behind national adoption of trusted identity services.

## Slide 34: Discovery Focus | Defining Queensland's Participation Model
Proposed solution
Queensland would:
Build a secure connection to NDLFRS
Upload driver licence images and biographic information
Establish continuous synchronisation processes
Enable Queensland licence participation in FVS checks
Receive transaction-based funding for verification usage.
High-Level Indicative View
Area Current Understanding
Build Cost $1.5M-$2.5M
Delivery Timeframe 1-2 years
Revenue Model $0.30 per verification transaction
Cost Recovery Approximately 3 years depending on uptake
Operating Model Ongoing maintenance and synchronisation required
Expected Benefits
✅ Improved identity assurance
✅ Reduced fraud and impersonation risk
✅ Improved privacy protections
✅ Support for national identity services
✅ Sustainable transaction-based funding model
✅ Reduced long-term revenue loss associated with replacement licences resulting from data breaches.
Key discovery questions
Data Scope & Eligibility
Which licence holders should be included?
Current licence holders only?
Expired or suspended licences?
Other licence statuses?
Lifecycle & Synchronisation
What occurs when licences are cancelled?
What occurs when customers transfer interstate?
How are data updates managed?
Privacy & Sensitive Customers
How are protected or suppressed customers handled?
What information can be shared?
What consent mechanisms are required?
Governance & Ownership
Who owns implementation?
Who funds ongoing operations?
What responsibilities sit with Commonwealth, TMR and service providers?
What ongoing support capability is required?